## Sheet1
ID | Type | Description / Suggestions | Creation Date | Status | Comment from Developer | Created_By
1 | Suggestion | 1. The requirement of a ‘valid URL’ needing “Medtronic.com” present, is not sufficient. Please find below the Medtronic sites where the feedback tool is not active. There are several other sites that do not specifically have “Medtronic.com” that we would want the feedback tool active. Can we have the requirement state that the URL needs to mention “Medtronic” and ensure it can parse the word, so when it says “Medtronicprod” that it still recognizes the “Medtronic” and activates the feedback tool. IT Service Portal - https://medtronicprod.service-now.com/it/ Service Now - https://medtronicprod.service-now.com/nav_to.do?uri=%2Fhome.do%3F Workday - https://www.myworkday.com/medtronic/d/home.htmld Cornerstone - https://medtronic.csod.com/ui/lms-learner-home/home?tab_page_id=-200300006&tab_id=-2 HR Portal - https://medtronicprod.service-now.com/hr/ Inside Medtronic - https://medtronic.sharepoint.com/sites/MDT/pages/home.aspx | 2019-05-08 | Resolved | medtronic keyword condition added | Christina
2 | Suggestion | Remove second window, highlighted in yellow below. Once the user clicks 'send' or 'Close' the main window should close. The second window is redudant and adds an additional unwanted click | 2019-05-08 | Resolved |  | Christina
3 | Suggestion | Please enable the area highlighted yellow to trigger a selection. Right now the user can only click on the smiley or frown face to trigger a selection, we want the user to click on the verbiage as well to trigger the selection. | 2019-05-08 | Resolved | row wise selection added | Christina
4 | Defect | This times are not accurate for when I sent the feedback? Sent the feedback at 3:44pm my time and the below report shows 2:13 | 2019-05-08 | Resolved | currently server is capturing the time, chnages added to receive time from browsers | Christina